## Sheet1
Priyanka | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | Backend servers created and designing UI Wireframes and updating the journal
|  | What am I planning to do to next? | updated the weekly scrum report, updated the UI wireframes, and begin front end development for the app, the home page, login, and register pages were finished, and the weekly scrum report was updated.
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | Start building user interface for member home page screen, Login and Register Page,Integrate Login and Register page with backend
|  | What am I planning to do to next? | completing integrating the backend with the login and registration pages and updated the weekly scrum report
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | Implement and integrate functionality based on trails and booking availability and locations
|  | What am I planning to do to next? | completed all functionality, including all features and integrating the backend, and updated the weekly Scrum report.
|  | What tasks are blocked waiting on another team member? | None
| Sprint 4 | What task did I work on/complete? | work on bug fixes
|  | What am I planning to do to next? | Integrating frontend with backend.
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | Integrated frontend with backend.
|  | What task did I work on/complete? | Journal Ended
|  | What tasks are blocked waiting on another team member? | None
Sri akhil | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | UI Wireframes were designed as part of work on updating the sprint journal and the weekly scrum report.
|  | What am I planning to do to next? | UI Wireframes should be updated, and front end development should begin.
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | updated the weekly scrum report, updated the UI wireframes, and began front end development
|  | What am I planning to do to next? | worked on UI Pages
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | Finished building UI Pages Admin
|  | What am I planning to do to next? | APIs and UI functionality will be integrated based on Roles .Implemented the UI and functionality of API for member
|  | What tasks are blocked waiting on another team member? | None
| Sprint 4 | What task did I work on/complete? | worked on login, signup Screen,Implemented the UI
|  | What am I planning to do to next? | Integrated the the UI with backend API
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | Worked on API integration and UI for update schedule,worked on All remaining functionalities.
|  | What am I planning to do to next? | Jorunal End
|  | What tasks are blocked waiting on another team member? | None
Jayanth | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | Worked on MongoDB and Updated Weekly scrum report
|  | What am I planning to do to next? | Mongodb schemas has to be created.
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | schema has been created for all functionalities.
|  | What am I planning to do to next? | Work on API calls
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | api call testing check
|  | What am I planning to do to next? | completing all functionalities with all features.
|  | What tasks are blocked waiting on another team member? | None
| Sprint 4 | What task did I work on/complete? | completied functionality including all features and integrating the backend, and updated the weekly Scrum report,updated journal
|  | What am I planning to do to next? | deployment
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | deploying application to the ec2, updated Readme.MD
|  | What am I planning to do to next? | Sprint End
|  | What tasks are blocked waiting on another team member? | None
Sanketh | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | Created mongodb schema which can be used as a object model and updating the journal.
|  | What am I planning to do to next? | create mongodb tables
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | created mongo tables, collections, basic views.
|  | What am I planning to do to next? | UI-login functionality
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | created UI-login functionality
|  | What am I planning to do to next? | Member login page has to be created
|  | What tasks are blocked waiting on another team member? | None
| Sprint 4 | What task did I work on/complete? | Created member login page
|  | What am I planning to do to next? | setup load balancer and deployment part.
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | Setting up load balancing, setting up auto scaled ec2 cluster and updated the journal and scrum report.
|  | What am I planning to do to next? | Sprint End
|  | What tasks are blocked waiting on another team member? | None